| Enclosure (8) PLANNING GUIDE LEGEND: Active Support Detachment = ACDET Community Support Event = CSE Exercise = Ex. Ft Pickett, VA = FPVA Major Subordinate Command = MSC (COMMBN/RGT) Multiple Unit Training Assembly = MUTA Operations Officer = OPSO = Op. Operations Order = OPORD Training Officer = TRNGO Warning Order = WARNO *“or” below applies when MSC is lead, rather than FORHQ. * If “S” shop does not exist at MSC, seek FORHQ assistance. |
| --- |
| TASK | PLANNER | WHEN | DONE | GENERAL NOTES |
| Yearly Training Plan (YTP) Schedule | G3 TRNGO w/ MSC S3s/CDR Input | 1 Jan each CY |  | See O&T SOP, YT Calendar due 1 Oct and YTP planning begins 1 Nov. |
| FPVA building reservations | G3 OPSO w/ ACTDET input | 6-12 months prior when possible |  | Barracks, classrooms, admin. Special Note 1 |
| Liaison with CSE/Ex. Partners | G3 OPSO or MSC S3/CDR if lead | 4-6 months prior |  | Confirm 2 months prior & two weeks prior. |
| FPVA VIP Billeting | G4 | 4 months prior |  | Special Note 1. Confirm 2 months prior & two weeks prior. |
| CSE or VANG Support Req. Notice | G3 OPSO or MSC S3/CDR thru G3 | 4 months prior |  | See O&T SOP Encl (7) or (7A). Special Note 2 |
| Initial monthly OPS Brief for CG (MUTA/Ex.) | G3 OPSO | 4 months prior |  |  |
| WARNO for MUTA/CSE/Ex./Op. | G3 OPSO or MSC S3/CDR if | 4 months prior |  | More complexity = more lead time. Special Note 3 |
| Rental vehicles request | G4 or MSC S4 if MSC | 3 months prior |  | To ACTDET. Verify 7 days prior. |
| Food Services Contract request | G4 or MSC S4 if MSC | 3 months prior |  | To ACTDET. Verify 7 days prior. Special Note 5. |
| Printing Contract (go/no-go sheets; sign-in sheets, class materials, etc. | G4 or S MSC 4 if MSC | 3 months prior |  | To ACTDET |
| MSC req to FORHQ for Comm, log, admin etc. support | G3 OPSO or MSC S3/CDR if MSC | 3 months prior |  | Made to Signal Battalion for MCP/IMAR/PITPAC & G3 for STARS or Wouxun handheld. Special Note 4 |
| CSE MOU draft to JFHQ | G3 OPSO or MSC S3/CDR thru G3 | 2 months prior to signing |  | Coordinating discussions for CSE are not an MOU. |
| Class Planned; Instr/A-Instrs lined up; material QA’d | G3 TRNGO w/ MSC S3/CDRs if lead | 2 months prior |  | Program of Instruction, Lesson Plan, slides, handouts; sign-in sheets, training aids, rehearsals |
| MSC MUTA and class attendance raw numbers Rosters to ACTDET | MSC | 2 months prior |  |  |
| Exercise Detailed Planning | G3 OPSO or MSC S3/CDR if lead | 2 months prior |  | Force composition; Master Scenario Events List (MESL); Red Cell; White Cell |
| Operation Risk Assessment (ORA) DD 2799 | G3 OPSO or MSC S3/CDR if MSC | 2 months prior |  | Minimally consider weather; terrain; traffic (to/from/in); vectors; equipment uses; physical requirements |
| PERSSTAT/LOGSTAT & Support Requests | G1, G4 or MSC S4 if MSC | 2 months prior |  | To G4/ACTDET (if money involved). MREs, water; equipment; etc. to ACTDET. Special Note 4. |
| MSC MUTA and class attendance raw numbers Rosters to ACTDET | MSC | 2 months prior |  |  |
| MSC MUTA attendance by-name rosters to ACTDET | MSC | 1 month prior |  |  |
| MSC MUTA IET &MOS class attendance by-name rosters to ACTDET | MSC | 1 month prior |  |  |
| OPORD/FRAGO for MUTA/CSE/Ex./Op. | G3 OPSO or MSC S3/CDR if lead | 1 month prior |  | Limit additional FRAGOs as much as possible |
| OPORD/FRAGO Annex C (Operations) | G3 OPSO or MSC S3/CDR if MSC | 1 month prior |  | Usually for an Ex. Within a MUTA. Annex K (Civil Support may also or instead be considered. |
| OPORD/FRAGO Annex F (Sustainment) | G1/G4 or MSC S1/S4 if MSC | 1 month prior |  | G1/G4 lead; will include Chaplain, Medical, Transportation, Logistics, (Food Services, General Supply Classes) |
| OPORD/FRAGO Annex H (Signal) | G6 or MSC S6 if MSC | 1 month prior |  | Appendix 1– Guard Chart; Appendix 2– ICS Form 205A (POCs); Appendix 3- Safety Worksheet; Appendix 4- Freq Req.; Appendix 5- MCP Locations |
| Vehicle/MCP/Equipment check/maintenance | G4/Signal Battalion/S4 | 1 month prior |  |  |
| MCPs exercise single-channel check | Signal Battalion | 1 month prior |  | When MCPs used w/ base station & 2 antennas |
| Each MCP demonstrate ability to send a data message to a pre-designated email account | Signal Battalion | 1 month prior |  | When MCPs will be used |
| Class rosters and sign in sheets | G3 TRNGO or MSC S3/CDR if MSC lead | 1month prior |  |  |
| Barrack assignments | G4 or MSC S4 if MSC lead | 1 month prior |  | Work with TRNGO if by instruction group |
| MUTA honors/formation discussion | CSMs lead and G1/G3 info | 1 month prior |  | Awards; inductions; retirements; presentations |
| Training Schedule (TS) | G3 OPSO/TRNGO or MSC S3/CDR if MSC lead | 1 month prior |  | Need to coordinate with all affected parties and Commander approve |
| MSC/HQ Orders (if TS is not orders), including Advance Party | G1 or MSC S1 if MSC lead | 14 days prior |  | Provide G1/S1 a roster in first, last, MI and VDF ID# |
| Movement Plans | CO Cdrs to MSC S3/CDR/G3 | 7 days prior |  |  |
| Range/Safety rep meeting | G3 OPSO or MSC S3/CDR if MSC lead | 2 days prior |  | Attend range/SafetyO meeting at FPVA or other installations to review activities. |
| Advance Party | G3 OPSO or MSC S3/CDR if MSC | 1-2 days prior |  | Confirm ORA; if buildings rented, heck out keys & inspect buildings; contact food services vender to verify schedule and # meals; prepare HQ, including sign-in sheets and TOC |
| Check in-out with JOC | G3 OPSO or MSC S3/CDR if MSC | Day of Event |  | See SOP for number |
| AAR due | MSC S3/CDR | 7 days after |  |  |

SPECIAL NOTES:

1.  Same schedule if using A.P. Hill, Camp Pendleton, etc.

2. O&T SOP encl (7) is CSE notice to JOC (PIO) and encl (7A) is Support Request to J3

3.  Everything required in the OPORD should be ordered to be planned by the WARNO4.

4.  Units requesting equipment from FORHQ are responsible for pickup and return of the equipment.  This also includes cost of parcel post and UPS for big bulky items if can't transport it in person.

5.  Rough numbers 2 months prior and by –full-name list 1 month prior